## Level of Effort Chart
Organisation name:
Activity start and end dates:
LEVEL OF EFFORT CHART
# | Milestone | Personnel | [11 empty] | Total days | Sub Total days remote | Sub Total days on the ground
|  | Project Manager/ Scrum Master | Business Analyst/ System Architect | Team Leader/ Senior software developer | Other Key or Non Key Expert | Other Key or Non Key Expert | Other Key or Non Key Expert | Other Key or Non Key Expert | Other Key or Non Key Expert | Other Key or Non Key Expert | Other Key or Non Key Expert | ... | …
1. | Milestone 1. Project preparation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Activity 1.1: Project kick-off meeting | [12 empty] | 0 | 0 | 0
| Activity 1.2: Developing the Project Management and Implementation Plan | [12 empty] | 0 | 0 | 0
| Activity 1.3: Preliminary business analysis and detailed design (SRS and SDD documents) of the SIMIDA | [12 empty] | 0 | 0 | 0
| Activity 1.4: Preparing requirements for SIMIDA hosting infrastructure (for development, testing/training, and production environments) | [12 empty] | 0 | 0 | 0
2. | Milestone 2. Design and development of the SIMIDA components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 2.1: Preparation of the product backlog for the development of the SIMIDA
Activity 2.2: Configuring the hosting infrastructure (development and testing/training environments)
| Activity 2.3: Iterative and incremental implementation of SIMIDA component ISS „Register of Food Chain Operators” using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | [12 empty] | 0 | 0 | 0
| Activity 2.4: Iterative and incremental implementation of SIMIDA component ISS "Import Monitoring and Control" using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | [12 empty] | 0 | 0 | 0
| Activity 2.5: Iterative and incremental implementation of SIMIDA component ISS "Recording and Dissemination of Alerts" using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | [12 empty] | 0 | 0 | 0
| Activity 2.6: Iterative and incremental implementation of SIMIDA component „Administration and system functionalities” using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | [12 empty] | 0 | 0 | 0
| Activity 2.7: Iterative and incremental implementation of SIMIDA Front Office component „Public portal of ANSA” using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | [12 empty] | 0 | 0 | 0
| Activity 2.8: Hold design workshops or individual sessions with stakeholders to define the next sprint backlogs, and to validate the SIMIDA components design/functionalities and important project decisions. | [12 empty] | 0 | 0 | 0
Activity 2.9: Internal testing (manual and automated) of the software functionalities implemented during each iteration.
| Activity 2.10: Periodical demo presentations, training on how to use the implemented functionalities and consultation on the SIMIDA usability. Provide to stakeholders the prototype versions of the SIMIDA to allow the opportunity to review and provide comments. | [12 empty] | 0 | 0 | 0
| Activity 2.11: Weekly project management status meetings, to report and discuss the overall project status, issues, achievements and planned activities, milestones, deliverables, and project risks. | [12 empty] | 0 | 0 | 0
3. | Milestone 3. Integration of the SIMIDA with external IT Systems | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ... | 0 | 0 | 0 | 0
| Activity 3.1:Integration of the SIMIDA with governmental shared platforms (MPass, MSign, MNotify, MPower, MLog, PGD). | [12 empty] | 0 | 0 | 0
| Activity 3.2: Integration of the SIMIDA with RM state registers (RSP, RSUD, RBI, RSV, RSC). | [12 empty] | 0 | 0 | 0
| Activity 3.3: Integration of the SIMIDA with PDSE, SIA GEAP and other IT systems of public authorities. | [12 empty] | 0 | 0 | 0
Activity 3.4: Development of the SIMIDA APIs to provide data to external IT Systems.
| Activity 3.5: Testing the integrations between the SIMIDA components and external information systems. | [12 empty] | 0 | 0 | 0
4. | Milestone 4. Data migration and data population | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ... | 0 | 0 | 0 | 0
| Activity 4.1: Developing the data migration plan. | [12 empty] | 0 | 0 | 0
| Activity 4.2: Developing the data migration and data population scripts. | [12 empty] | 0 | 0 | 0
| Activity 4.3: Performing data migration and data population. | [12 empty] | 0 | 0 | 0
| Activity 4.4: Testing and approving the migrated and populated data. | [12 empty] | 0 | 0 | 0
5. | Milestone 5. Training of users | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ... | 0 | 0 | 0 | 0
| Activity 5.1: Developing the training plan and schedule. | [12 empty] | 0 | 0 | 0
| Activity 5.2: Developing the support materials required for the training of the authorized users. | [12 empty] | 0 | 0 | 0
| Activity 5.3: Training of System Administrators and the personnel responsible for technical administration. | [12 empty] | 0 | 0 | 0
| Activity 5.4: Training of all categories of authorized users. | [12 empty] | 0 | 0 | 0
6. | Milestone 6. SIMIDA stabilization and acceptance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ... | 0 | 0 | 0 | 0
| Activity 6.1: Making changes to improve the SIMIDA components usability based on the feedback received during the user training and from stakeholders’ representatives. | [12 empty] | 0 | 0 | 0
| Activity 6.5: Stabilization of the SIMIDA (applying improvements, bug fixing, technical support and assistance). | [12 empty] | 0 | 0 | 0
| Activity 6.3: Making the required updates to technical and user documentation based on the SIMIDA improvements. | [12 empty] | 0 | 0 | 0
| Activity 6.4: Final User Acceptance Testing of the SIMIDA according to already developed and approved test scenarios and test cases. | [12 empty] | 0 | 0 | 0
| Activity 6.5: SIMIDA handover activities. | [12 empty] | 0 | 0 | 0
7. | Milestone 7: Post-implementation Support and Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ... | 0 | 0 | 0 | 0
| Activity 7.1: Post-implementation support and maintenance activities after the stabilization and final acceptance period. | [12 empty] | 0 | 0 | 0
| Activity 7.2: Correcting shortcomings and updating SIMIDA on a regular basis, including all required updates for technical and user documentation. | [12 empty] | 0 | 0 | 0
GRAND TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ... | 0 | 0 | 0 | 0