## Work plan & input schedule
Organisation name:
Activity start and end dates:
WORKPLAN
| Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22 | Month 23 | Month 24 | Month 25 | Month 26 | Month 27 | Month 28 | Month 29 | Month 30 | Month 31
Milestone 1. Project preparation | bar: Year 1 Month 1 to Year 1 Month 2
Activity 1.1: Project kick-off meeting | bar: Year 1 Month 1
Activity 1.2: Developing the Project Management and Implementation Plan | bar: Year 1 Month 1
Activity 1.3: Preliminary business analysis and detailed design (SRS and SDD documents) of the SIMIDA | bar: Year 1 Month 1 to Year 1 Month 2
Activity 1.4: Preparing requirements for SIMIDA hosting infrastructure (for development, testing/training, and production environments) | bar: Year 1 Month 1
Milestone 2. Design and development of the SIMIDA | bar: Year 1 Month 3 to Year 2 Month 14
Activity 2.1: Preparation of the product backlog for the development of the SIMIDA | bar: Year 1 Month 3 to Year 2 Month 14
Activity 2.2: Configuring the hosting infrastructure (development and testing/training environments) | bar: Year 1 Month 3
Activity 2.3: Iterative and incremental implementation of SIMIDA component ISS „Register of Food Chain Operators” using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | bar: Year 1 Month 3 to Year 1 Month 10
Activity 2.4: Iterative and incremental implementation of SIMIDA component ISS "Import Monitoring and Control" using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | bar: Year 1 Month 4 to Year 2 Month 13
Activity 2.5: Iterative and incremental implementation of SIMIDA component ISS "Recording and Dissemination of Alerts" using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | bar: Year 1 Month 4 to Year 1 Month 12
Activity 2.6: Iterative and incremental implementation of SIMIDA component „Administration and system functionalities” using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | bar: Year 1 Month 3 to Year 1 Month 11
Activity 2.7: Iterative and incremental implementation of SIMIDA Front Office component „Public portal of ANSA” using agile PM approach, and Continuous Integration/Continuous Delivery practices Developing and updating the technical documentation during each iteration/sprint. | bar: Year 1 Month 9 to Year 2 Month 14
Activity 2.8: Hold design workshops or individual sessions with stakeholders to define the next sprint backlogs, and to validate the SIMIDA components design/functionalities and important project decisions.
Activity 2.9: Internal testing (manual and automated) of the software functionalities implemented during each iteration.
Activity 2.10: Periodical demo presentations, training on how to use the implemented functionalities and consultation on the SIMIDA usability. Provide to stakeholders the prototype versions of the SIMIDA to allow the opportunity to review and provide comments.
Activity 2.11: Weekly project management status meetings, to report and discuss the overall project status, issues, achievements and planned activities, milestones, deliverables, and project risks.
Milestone 3. Integration of the SIMIDA with external IT Systems | bar: Year 1 Month 4 to Year 1 Month 10
Activity 3.1:Integration of the SIMIDA with governmental shared platforms (MPass, MSign, MNotify, MPower, MLog, PGD).
Activity 3.2: Integration of the SIMIDA with RM state registers (RSP, RSUD, RBI, RSV, RSC).
Activity 3.3: Integration of the SIMIDA with PDSE, SIA GEAP and other IT systems of public authorities.
Activity 3.4: Development of the SIMIDA APIs to provide data to external IT Systems.
Activity 3.5: Testing the integrations between the SIMIDA components and external information systems.
Milestone 4. Data migration and data population | bar: Year 1 Month 11 to Year 2 Month 15
Activity 4.1: Developing the data migration plan.
Activity 4.2: Developing the data migration and data population scripts.
Activity 4.3: Performing data migration and data population.
Activity 4.4: Testing and approving the migrated and populated data.
Milestone 5. Training of users | bar: Year 2 Month 16
Activity 5.1: Developing the training plan and schedule.
Activity 5.2: Developing the support materials required for the training of the authorized users.
Activity 5.3: Training of System Administrators and the personnel responsible for technical administration.
Activity 5.4: Training of all categories of authorized users.
Milestone 6. SIMIDA stabilization and acceptance | bar: Year 2 Month 17 to Year 2 Month 19
Activity 6.1: Making changes to improve the SIMIDA components usability based on the feedback received during the user training and from stakeholders’ representatives.
Activity 6.2: Stabilization of the SIMIDA (applying improvements, bug fixing, technical support and assistance).
Activity 6.3: Making the required updates to technical and user documentation based on the SIMIDA improvements.
Activity 6.4: Final User Acceptance Testing of the SIMIDA according to already developed and approved test scenarios and test cases.
Activity 6.5: SIMIDA handover activities.
Milestone 7: Post-implementation Support and Maintenance | bar: Year 2 Month 20 to Year 3 Month 31
Activity 7.1: Post-implementation support and maintenance activities after the stabilization and final acceptance period.
Activity 7.2: Correcting shortcomings and updating SIMIDA on a regular basis, including all required updates for technical and user documentation.
PROJECT KEY DELIVERABLES
Milestone 1 Deliverables
Deliverable 1.1. Kick-off meeting presentation and Project Initiation/Charter document. | bar: Year 1 Month 1
Deliverable 1.2. Project Management Plan. | bar: Year 1 Month 1
Deliverable 1.3. SRS and SDD of SIMIDA. | bar: Year 1 Month 2
Deliverable 1.4. Requirements for SIMIDA hosting infrastructure. | bar: Year 1 Month 2
Milestone 2 Deliverables
Deliverable 2.1. SIMIDA product backlog. | bar: Year 1 Month 3 to Year 2 Month 14
Deliverable 2.2. Approved report on configured hosting infrastructure for SIMIDA. | bar: Year 1 Month 3
Deliverable 2.3. Updated SDD of SIMIDA. | bar: Year 1 Month 3 to Year 2 Month 14
Deliverable 2.4. Approved report on the deployed functional SIMIDA components on the development, testing/training and production environments. | bar: Year 1 Month 10 to Year 2 Month 14
Deliverable 2.5. Full source code of the developed SIMIDA. | bar: Year 2 Month 14
Deliverable 2.6. Weekly project management status reports. | bar: Year 1 Month 3 to Year 2 Month 14
Milestone 3 Deliverables
Deliverable 3.1. Detailed plan for integrating SIMIDA with external information systems. | bar: Year 1 Month 4
Deliverable 3.2. Technical specifications for each integration. | bar: Year 1 Month 6
Deliverable 3.3. Documentation of the implemented SIMIDA application programming interfaces (APIs). | bar: Year 1 Month 8
Deliverable 3.4. Report and acceptance of the implemented interoperability and data exchange mechanism. | bar: Year 1 Month 10
Milestone 4 Deliverables
Deliverable 4.1. Data migration methodology and plan. | bar: Year 1 Month 11
Deliverable 4.2. Data migration/transformation scripts. | bar: Year 2 Month 13
Deliverable 4.3. Data transformation and migration approved report. | bar: Year 2 Month 15
Milestone 5 Deliverables
Deliverable 5.1. Training plan with schedule. | bar: Year 2 Month 15
Deliverable 5.2. Training materials. | bar: Year 2 Month 15
Deliverable 5.3. Report on conducted trainings. | bar: Year 2 Month 16
Deliverable 5.4. Report on provided access to the helpdesk service. | bar: Year 2 Month 16
Milestone 6 Deliverables
Deliverable 6.1. Updated SDD of SIMIDA. | bar: Year 2 Month 19
Deliverable 6.2. Report on conducted change management and outreach activities, corrected shortcomings and updated technical and user documentation. | bar: Year 2 Month 19
Deliverable 6.3: Components within the SIMIDA perimeter that are operational and running in the production environment | bar: Year 2 Month 19
Deliverable 6.4. Final User Acceptance Test report. | bar: Year 2 Month 19
Deliverable 6.5. Minutes for the handover of the SIMIDA to the ANSA with associated documentation. | bar: Year 2 Month 19
Milestone 7 Deliverables
Deliverable 7.1. Monthly reports on support and maintenance, including the number of helpdesk requests and maintenance as well as support indicators according to the SLA requirements. | bar: Year 2 Month 20 to Year 3 Month 31
Deliverable 7.2. Report on corrected shortcomings and updated technical and user documentation, including the SIMIDA updated source code | bar: Year 2 Month 20 to Year 3 Month 31
▲ denotes formal deliverable